## Project Planner
Gantt
ACTIVITY | Description | EST | LFT | PLAN START | PLAN DURATION | Workers Required | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Activity 01 | Establish site office | 1 | 3 | 1 | 3 | 3 | PERIODS 1: TRUE; PERIODS 2: TRUE; PERIODS 3: TRUE
Activity 02 | Clear topsoil from site | 4 | 6 | 4 | 3 | 6 | PERIODS 4: TRUE; PERIODS 5: TRUE; PERIODS 6: TRUE
Activity 03 | Order steelwork | 1 | 2 | 1 | 2 | 1 | PERIODS 1: TRUE; PERIODS 2: TRUE
Activity 04 | Fabricate steelwork offsite | 3 | 16 | 3 | 14 | 8 | PERIODS 3: TRUE; PERIODS 4: TRUE; PERIODS 5: TRUE; PERIODS 6: TRUE; PERIODS 7: TRUE; PERIODS 8: TRUE; PERIODS 9: TRUE; PERIODS 10: TRUE; PERIODS 11: TRUE; PERIODS 12: TRUE; PERIODS 13: TRUE; PERIODS 14: TRUE; PERIODS 15: TRUE; PERIODS 16: TRUE
Activity 05 | Deliver steelwork to the site | 17 | 23 | 17 | 2 | 4 | PERIODS 17: TRUE; PERIODS 18: TRUE; PERIODS 19: FALSE; PERIODS 20: FALSE; PERIODS 21: FALSE; PERIODS 22: FALSE; PERIODS 23: FALSE
Activity 06 | Order steel reinforcement | 1 | 2 | 1 | 2 | 1 | PERIODS 1: TRUE; PERIODS 2: TRUE
Activity 07 | Fabricate steel reinforcement offsite | 3 | 9 | 3 | 7 | 6 | PERIODS 3: TRUE; PERIODS 4: TRUE; PERIODS 5: TRUE; PERIODS 6: TRUE; PERIODS 7: TRUE; PERIODS 8: TRUE; PERIODS 9: TRUE
Activity 08 | Deliver steel reinforcement to site | 10 | 10 | 10 | 1 | 2 | PERIODS 10: TRUE
Activity 09 | Deliver cladding to site | 4 | 31 | 4 | 1 | 2 | PERIODS 4: FALSE; PERIODS 5: FALSE; PERIODS 6: FALSE; PERIODS 7: FALSE; PERIODS 8: FALSE; PERIODS 9: FALSE; PERIODS 10: FALSE; PERIODS 11: FALSE; PERIODS 12: FALSE; PERIODS 13: FALSE; PERIODS 14: FALSE; PERIODS 15: FALSE; PERIODS 16: FALSE; PERIODS 17: FALSE; PERIODS 18: FALSE; PERIODS 19: TRUE; PERIODS 20: FALSE; PERIODS 21: FALSE; PERIODS 22: FALSE; PERIODS 23: FALSE; PERIODS 24: FALSE; PERIODS 25: FALSE; PERIODS 26: FALSE; PERIODS 27: FALSE; PERIODS 28: FALSE; PERIODS 29: FALSE; PERIODS 30: FALSE; PERIODS 31: FALSE
Activity 10 | Excavate for foundations and floorslab | 7 | 10 | 7 | 4 | 7 | PERIODS 7: TRUE; PERIODS 8: TRUE; PERIODS 9: TRUE; PERIODS 10: TRUE
Activity 11 | Place reinforcement for foundations and floor slab | 11 | 14 | 11 | 4 | 6 | PERIODS 11: TRUE; PERIODS 12: TRUE; PERIODS 13: TRUE; PERIODS 14: TRUE
Activity 12 | Pour concrete in foundations and floor slab | 15 | 16 | 15 | 2 | 6 | PERIODS 15: TRUE; PERIODS 16: TRUE
Activity 13 | Cure concrete | 17 | 23 | 17 | 7 | 0 | PERIODS 17: TRUE; PERIODS 18: TRUE; PERIODS 19: TRUE; PERIODS 20: TRUE; PERIODS 21: TRUE; PERIODS 22: TRUE; PERIODS 23: TRUE
Activity 14 | Erect steelwork | 24 | 31 | 24 | 8 | 10 | PERIODS 24: TRUE; PERIODS 25: TRUE; PERIODS 26: TRUE; PERIODS 27: TRUE; PERIODS 28: TRUE; PERIODS 29: TRUE; PERIODS 30: TRUE; PERIODS 31: TRUE
Activity 15 | Place cladding on steelwork | 32 | 35 | 32 | 4 | 5 | PERIODS 32: TRUE; PERIODS 33: TRUE; PERIODS 34: TRUE; PERIODS 35: TRUE
Activity 16 | Complete internal fit out of the building | 36 | 41 | 36 | 6 | 8 | PERIODS 36: TRUE; PERIODS 37: TRUE; PERIODS 38: TRUE; PERIODS 39: TRUE; PERIODS 40: TRUE; PERIODS 41: TRUE
Activity 17 | Clean up site | 42 | 43 | 42 | 2 | 4 | PERIODS 42: TRUE; PERIODS 43: TRUE
Activity 18 | Remove site office | 44 | 44 | 44 | 1 | 3 | PERIODS 44: TRUE
Workforce Requirements | [6 empty] | 5 | 5 | 17 | 20 | 20 | 20 | 21 | 21 | 21 | 17 | 14 | 14 | 14 | 14 | 14 | 14 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 4 | 3
Min completion time = 44